| DUE DATES | TASK | Details | SUCCESS CRITERIA | PROGRESS |
| --- | --- | --- | --- | --- |
| 19/9/2025 | Meet with personal projects supervisor to discuss about my product. | Why is creating a volleyball guidebook useful? What impact does it have on people? | - Aesthetics - Function - Impact | Complete |
| September 10th- September 30th | Research about how to create a book |  |  | Complete |
| September 30th | Create a mood board |  |  | Complete |
| October 1st | Create mockups on my products |  |  | Complete |
| October 9th-November 30th | Learn how to add information into a book |  |  | Complete |
| December 1st-December 14th | Starting the prototype and finishing the prototype. |  |  |  |
| December 16th | Receive feedback on how I can improve my prototype | Success criteria too general Actionplan insufficient details, no realistic planning Strand I requires refinement Strand 2 almost not yet started | PP-status insufficient, needs to restart | Compl. |
| December 20th | Analyse project approach, success possible? | Current approach makes success difficult: Small target group (experienced players) Book-format complicated, printing risk, No way to change after printing Not possible to check visitors Many volleyball books exist, how to make something new? | - Attract many readers - Easy to access - Exciting to watch/see - Avoid long text passages | Compl. |
| December 20th | Requirements biographie | Study format biographie requirements How to protect a webpage-copyright possible? | Requirements fulfilled | Compl. |
| December 30th | Define new approach | Change Target group Change format from book to web-page Add more volleyball specific information, next to excercises for students that play already | Focus on students, age-group 12 – 19; Make a working tool for schools, attaract students to play volleyball; Students who did not play yet (general info volleyball needed), ones who pay already (usefull excecised with video examplesneeded) Easy to access for young people; Changes up-dates can be added easier than with printing; Videos can be included; Usage for many schools possible be replacement of school dedicated webpage Visitors can be counted; Targeting newcomers, show that volleyball is a modern, popular and exciting sport Additional information : - Study history volleyball - Introduce rules volleyball - Introduce school specific information volleyball (ASA) - Show the volleyball is good for health - Introduce beach-volleyball as major reason for increased popularity - Show professional volleyball - Show top volleyball countries, clubs and leagues today | ongoing |
| Jan 10th | Study how to make a webpage | How to make a webpage, Structure Webpage | - Attractive design requirements - How to go online - How to avoid copyright problems (especially with images and videos) - How to count visitors - How to become visible online - Target 10 pages, if necesarry subpages - How to make animated elements, how to embed videos and images | ongoing |
| Jan 10th | Detailes excercises as heart of the webpage | How to present How to separate newcomers/experienced How to measure if any improvement? | - Explanantion combined with pics, videos or drawings - Consider excecise for technique, power, speed, endurance, all volleyball specific - Improvement in power or endurance can be checked, technics difficult | ongoing |
| Jan 10th | Collect information | Main source is web, books (if available), interviews (info EIS) | - Collect relevant webpages - Check if collected info are sufficient to create informative pages for the web - If not consider changes in the information to be provided | ongoing |
| Jan 10th | Complete creation of mockups | Based on collected information create mockups for single sides in the webpage | Mockups created that can be used to start coding of webpage | ongoing |
| Jan 30th | Completion demonstration videos | Coordination with school to get permission to work on the volleyball field | Add to webpage | open |
| January 24th -March 16th | Starting and finishing the actual product |  |  |  |